## Gantt Chart
5010 CEM
Inti
14/5/25
Spint No |  | Start Date | End Date | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
Planning
1 | Discussion/prototyping | 22/4/25 | 29/4/25
Core Development
2 | Program Design, User Registration, Login | 29/4/25 | 2025-06-05
3 | Product Browsing & Search, Shopping Cart | 2025-06-05 | 13/5/25
4 | Secure Checkout, Backend Development | 13/5/25 | 20/5/25
Admin Panels
5 | Product/Order Management (Admin) | 20/5/25 | 27/5/25
6 | Customer Management (Admin) | 27/5/25 | 2025-03-06
Enhancement
7 | Order Pickup Notification | 2025-03-06 | 2025-10-06
8 | Refined Developed Site | 2025-10-06 | 17/6/25
Testing & Launch
9 | Final Testing & Bug Fixes | 17/6/25 | 24/6/25
10 | Launch | 24/6/25 | 2025-01-07