## Sprint_Plan_Table
Sprint Number | Start Date | End Date | Tasks
Sprint 1 | 2025-04-22 | 2025-04-29 | Discussion, Prototyping
Sprint 2 | 2025-04-29 | 2025-05-06 | Program Design & Coding, User Registration & Login
Sprint 3 | 2025-05-06 | 2025-05-13 | Product Browsing & Search, Shopping Cart
Sprint 4 | 2025-05-13 | 2025-05-20 | Secure Checkout, Backend Development
Sprint 5 | 2025-05-20 | 2025-05-27 | Product Management (Admin), Order Management (Admin)
Sprint 6 | 2025-05-27 | 2025-06-03 | Customer Management (Admin)
Sprint 7 | 2025-06-03 | 2025-06-10 | Order Pickup Notification
Sprint 8 | 2025-06-10 | 2025-06-17 | Refine Developed Site
Sprint 9 | 2025-06-17 | 2025-06-24 | Final Testing and Bug Fixes
Sprint 10 | 2025-06-24 | 2025-07-01 | Launch
Task | Planned | Actual
Sprint 1 | 100 | 100
Sprint 2 | 90 | 80
Sprint 3 | 80 | 70
Sprint 4 | 60 | 50
Sprint 5 | 50 | 40
Sprint 6 | 40 | 30
Sprint 7 | 30 | 20
Sprint 8 | 20 | 10
Sprint 9 | 10 | 0
Sprint 10 | 0 | 0